## Sheet1
Person | Day Available (Less Personal Time) | Days for Other Scrum Activities | Hours per Day | Available Effort-Hours |  | Q1 - 2025 | Q2 - 2025 | Q3 - 2025
Jason | 10 | 2 | 5-7 | 40 - 56 | Market Map | Launch MVP | Expansion Planning | Strategic Partnerships
Charles | 9 | 2 | 5-6 | 35 - 42 | Feature/ Benefit Map | Account Creation, Transfers | Bill Payments, Loan Application | Investment Options
Nindy | 10 | 2 | 4-7 | 32 - 56 | Architecture Map | Basic Cloud Infrastructure | Security Enhancements
Ferdinan | 8 | 2 | 6-7 | 36 - 42 | Market Events | Fintech Summit 2025 | Digital Banking Expo
Total |  |  |  | 143 - 196 | Release Schedule | Version 0.5 | Version 0.8